## Sheet1
Wheels & Swingarm Actuated					Wheels Actuated					Wheels Actuated, No Zones					Wheels Actuated + Hydraulic Switchover

Wheel Actuators (Per row unit)				Mechanical Prototype		Matl’s	Eng. Hrs			Wheel Actuators (Per row unit)				Mechanical Prototype		Matl’s	Eng. Hrs			Wheel Actuators (Per row unit)				Mechanical Prototype		Matl’s	Eng. Hrs			Wheel Actuators (Per row unit)				Mechanical Prototype		Matl’s	Eng. Hrs
Component	Cost	Qty		Understand basic force requirements			4			Component	Cost	Qty		Understand basic force requirements			3			Component	Cost	Qty		Understand basic force requirements			3			Component	Cost	Qty		Understand basic force requirements			4
Brackets, Hardware	$50	1		Specify Motors			4			Brackets, Hardware	$50	1		Specify Motors			3			Brackets, Hardware	$50	1		Specify Motors			3			Brackets, Hardware	$50	1		Specify Motors			6
Gearmotor	$100	2		Design Driveline			16			Gearmotor	$100	2		Design Driveline			8			Gearmotor	$100	2		Design Driveline			8			Gearmotor	$100	2		Design Driveline			14
Driveline (Pulley, gears, etc.)	$80	2		Build Prototype (1 row unit)		$1,650	12			Driveline (Pulley, gears, etc.)	$80	2		Build Prototype (1 row unit)		$885	8			Driveline (Pulley, gears, etc.)	$80	2		Build Prototype (1 row unit)		$885	8			Driveline (Pulley, gears, etc.)	$80	2		Build Prototype (1 row unit)		$1,440	14
Sensor	$70	2		Test & Refine Prototype		$800	20			Sensor	$70	2		Test & Refine Prototype		$500	15			Sensor	$70	2		Test & Refine Prototype		$500	15			Sensor	$70	3		Test & Refine Prototype		$800	20
Cables	$10	4					Cables	$10	4					Cables	$10	4					Cables	$10	4

	Totals	$590				Total:	$6,930				Totals	$590				Total:	$4,345				Totals	$590				Total:	$4,345				Totals	$660				Total:	$6,880

Swingarm Actuator				Electrical Prototype		Matl’s	Eng. Hrs					Electrical Prototype		Matl’s	Eng. Hrs					Electrical Prototype		Matl’s	Eng. Hrs			Swingarm Actuator				Electrical Prototype		Matl’s	Eng. Hrs
Component	Cost	Qty		Specify Sensors			4					Specify Sensors			4					Specify Sensors			4			Component	Cost	Qty		Specify Sensors			4
Brackets, Hardware	$50	1		Design & Prototype RCU on Bench		$435	28					Design & Prototype RCU on Bench		$345	28					Design & Prototype RCU on Bench		$345	25			Brackets, Hardware	$50	1		Design & Prototype RCU on Bench		$345	28
Gearmotor	$250	1		Design & Prototype OI on Bench		$514	28					Design & Prototype OI on Bench		$464	28					Design & Prototype OI on Bench		$458	20			Hydraulic Cylinder	$150	1		Design & Prototype OI on Bench		$464	28
Driveline (Pulley, gears, etc.)	$120	1		Design Enclosures		$60	8					Design Enclosures		$60	8					Design Enclosures		$60	7			Hydraulic Hoses	$100	1		Design Enclosures		$60	8
Sensor	$70	1		Build Prototype (1 row unit)		$547	20					Build Prototype (1 row unit)		$462	20					Build Prototype (1 row unit)		$459	18					Build Prototype (1 row unit)		$462	18
Cables	$10	2		Test & Refine Prototype		$200	30					Test & Refine Prototype		$200	30					Test & Refine Prototype		$200	25					Test & Refine Prototype		$200	25

	Totals	$510				Total:	$11,196					Total:	$10,971					Total:	$9,442				Totals	$300				Total:	$10,411

Row Control Unit (RCU)				Preparation for Production		Matl’s	Eng. Hrs			Row Control Unit (RCU)				Preparation for Production		Matl’s	Eng. Hrs			Row Control Unit (RCU)				Preparation for Production		Matl’s	Eng. Hrs			Row Control Unit (RCU)				Preparation for Production		Matl’s	Eng. Hrs
Component	Cost	Qty					Component	Cost	Qty					Component	Cost	Qty					Component	Cost	Qty
Housing	$10	1		Build 3 row unit cultivator		$6,641	12			Housing	$10	1		Build 3 row unit cultivator		$4,038	12			Housing	$10	1		Build 3 row unit cultivator		$4,034	12			Housing	$10	1		Build 3 row unit cultivator		$5,703	12
Cables	$15	2					Cables	$15	2					Cables	$15	2					Cables	$15	2
Connectors	$4	10					Connectors	$4	10					Connectors	$4	10					Connectors	$4	10
Microcontroller	$30	1		Make Electrical Schematics			20			Microcontroller	$30	1		Make Electrical Schematics			16			Microcontroller	$30	1		Make Electrical Schematics			15			Microcontroller	$30	1		Make Electrical Schematics			20
Motor Controller	$60	3		Make Mechanical Drawings			8			Motor Controller	$60	2		Make Mechanical Drawings			8			Motor Controller	$60	2		Make Mechanical Drawings			8			Motor Controller	$60	2		Make Mechanical Drawings			8
				Handoff to Electrical Supplier(s)			25					Handoff to Electrical Supplier(s)			20					Handoff to Electrical Supplier(s)			18					Handoff to Supplier(s)			25
				Write Owner’s Manual			20					Write Owner’s Manual			20					Write Owner’s Manual			20					Write Owner’s Manual			20
	Totals	$290				Total:	$13,441				Totals	$230				Total:	$10,118				Totals	$230				Total:	$9,874				Totals	$230				Total:	$12,503

Operator Interface (OI)				Production Costs (Materials only - no assy, etc.)					Operator Interface (OI)				Production Costs (Materials only - no assy, etc.)					Operator Interface (OI)				Production Costs (Materials only - no assy, etc.)					Operator Interface (OI)				Production Costs (Materials only - no assy, etc.)
Component	Cost	Qty		Base Cost	$257					Component	Cost	Qty		Base Cost	$232					Component	Cost	Qty		Base Cost	$229					Component	Cost	Qty		Base Cost	$232
LCD Panel	$50	1		Per-row-unit cost	$1,390					LCD Panel	$50	1		Per-row-unit cost	$820					LCD Panel	$50	1		Per-row-unit cost	$820					LCD Panel	$50	1		Per-row-unit cost	$1,190
Microcontroller	$100	1		# of row units	3	13	25			Microcontroller	$80	1		# of row units	3	13	25			Microcontroller	$80	1		# of row units	3	13	25			Microcontroller	$80	1		# of row units	3	13	25
Housing	$40	1		Total System Cost	$4,427	$18,327	$35,007			Housing	$40	1		Total System Cost	$2,692	$10,892	$20,732			Housing	$40	1		Total System Cost	$2,689	$10,889	$20,729			Housing	$40	1		Total System Cost	$3,802	$15,702	$29,982
Connectors	$4	3					Connectors	$4	3					Connectors	$4	3					Connectors	$4	3
Cables	$15	3					Cables	$15	3					Cables	$15	3					Cables	$15	3
Switches	$1	10		Engineering Costs	Rate	$80	/hr			Switches	$1	5		Engineering Costs	Rate	$80	/hr			Switches	$1	2		Engineering Costs	Rate	$80	/hr			Switches	$1	5		Engineering Costs	Rate	$80	/hr
				Total Time	259	hr					Total Time	231	hr					Total Time	209	hr					Total Time	254	hr
	Totals	$257			Eng. Labor Cost	$20,720					Totals	$232			Eng. Labor Cost	$18,480					Totals	$229			Eng. Labor Cost	$16,720					Totals	$232			Eng. Labor Cost	$20,320
				Prototyping Materials	$10,847					Prototyping Materials	$6,954					Prototyping Materials	$6,941					Prototyping Materials	$9,474
				Total Engineering Est.	$31,567					Total Engineering Est.	$25,434					Total Engineering Est.	$23,661					Total Engineering Est.	$29,794